Annexure- 2

Nehru Yuva Kendra Sangathan

Department of Youth Affairs

Programs, Activities, Numbers and Timeline of the

Second Phase of Project “Catch The Rain, where it falls, when it falls”

for Water Conservation with support of National Water Mission,

Ministry of Jal Shakti, Govt. of India

Phase - II

| S.No | Program | Activities | No. of Activities | Month |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | October 2021 | November 2021 | December, 2021 | January, 2022 |
| 1. | Sensitization of NYKS Officials and Youth Volunteers | Briefing, Orientation, Sensitization and Feedback | Sensitized and motivated 623 DYO, Deputy Directors, State Directors and Regional Directors from all States/UTs of the country for achieving the objectives of JSA-II |  |  |  |  |
| 2. | Oath on Water Conservation and Buzz Creation | - Administering of Oath on Water Conservation - Buzz Creation- promotional hashtags | 31,150 Oath Taking (one program each in 50 villages of all 623 Districts) | 7,787 Programs | 7,787 Programs | 7,788 Programs | 7,788 Programs |
| 3. | Advocacy and Environment Building for participation and support for Water Conservation | - Advocacy through public representatives, PRIS, service providers, opinion leader and other stakeholders, - Buzz Creation- promotional hashtags - Wall Writing, Displaying of posters & promotional IEC materials | 62,300 Programs (2 Programs in each village x 50 villages x 623 Districts) | 15,575 Programs | 15,575 Programs | 15,575 Programs | 15,575 Programs |
| 4. | Community Work Camps on Voluntary basis | - De-silting of Water resources, - Digging & maintenance of water sources | 31,150 Programs (One program each in all 50 Villages x 623 Districts) in the mentioned categories & others | 7,788 Programs | 7,788 Programs | 7,787 Programs | 7,787 Programs |
| 5. | Awareness and Education | - Nukkad Nataks, Songs - Padyatra- plogging run, Prabhat Pheris & Rallies | 62,300 Programs (2 programs in each village x 50 villages x 623 Districts) | 15,575 Programs | 15,575 Programs | 15,575 Programs | 15,575 Programs |
| 6. | Community Mobilization and Motivation for carry forward the work of water conservation and Maintenance of Water Sources | - Personal Contact and Social Media outreach for motivation of family members, PRIs, Farmers and Others | 31.15 Lakh Families (10 Members of a Youth Club in each village will mobilize 100 families in a village x 50 Villages x 623 Districts) | 8 Lakh | 8 Lakh | 7.5 Lakh | 7.5 Lakh |
| 7. | Jal Samvad/Jal Chaupals | - Talks and Dialogues with subject experts and motivators | 31,150 Programs (One program each in all 50 Villages x 623 Districts) | 7,788 Programs | 7,788 Programs | 7,787 Programs | 7,787 Programs |
| 8. | Knowledge Competition | - Quiz, poster making, painting and Slogan Writing competitions | 3,115 Programs (One programs each on a cluster of 10 villages) |  | 1,038 Programs | 1,038 Programs | 1,039 Programs |